## Week 2
KẾ HOẠCH W2–W4 • Work Package level • Action Plan chi tiết sẽ lập riêng theo từng tuần và theo dõi trên GitHub Projects
ID | Tuần | Work Package | Workstream | Ưu tiên | Gate-Critical | Owner (R) | Hỗ trợ | Effort (MD) | Start Date | End Date | Phụ thuộc / điều kiện | Status | Evidence Link | GitHub Issue
W2.01 | W2 | WBS baseline W1–W4, nhịp Action Plan tuần, Risk/Decision Log | PM / Governance | Must | Y | Đức | Bách Sỹ | 2.0 | 2026-10-20 | 2026-10-21 | Charter v1.1 | NOT STARTED
W2.02 | W2 | Chốt use case tư vấn BHNT và inventory tài liệu Prudential | BA / Policy | Must | Y | Bách Sỹ | Đức | 2.0 | 2026-10-20 | 2026-10-21 | Scope W1; tài liệu public | NOT STARTED
W2.03 | W2 | Checklist v0.1 và scenario mẫu (đúng / sai / thiếu thông tin) | BA / Policy | Must | N | Bách Sỹ | Trọng Nhân | 2.0 | 2026-10-21 | 2026-10-23 | W2.02 (soft: dùng giả định rõ) | NOT STARTED
W2.04 | W2 | Thử khả năng truy cập HF/public Voice datasets; rà license | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-20 | 2026-10-21 | Không chờ AI selection | NOT STARTED
W2.05 | W2 | Thiết kế dữ liệu TTS/role-play, transcript & ground-truth template | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2.0 | 2026-10-21 | 2026-10-23 | Kịch bản mock hợp lệ | NOT STARTED
W2.06 | W2 | OSS research VAD/ASR: Silero, Faster-Whisper, PhoWhisper; backup & license | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-20 | 2026-10-21 | W1 shortlist sơ bộ | NOT STARTED
W2.07 | W2 | OSS research Diarization/Emotion: primary, backup, librosa/openSMILE & license | Speech AI / OSS | Must | Y | Lê Huy | Thiên Long | 2.0 | 2026-10-21 | 2026-10-23 | Song song W2.06 | NOT STARTED
W2.08 | W2 | Phác thảo architecture, adapter boundaries, Job/Transcript contracts | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Hải Đăng | 2.0 | 2026-10-20 | 2026-10-21 | Fixture mock chưa cần model thật | NOT STARTED
W2.09 | W2 | BE mock job/status endpoint proof và đề xuất stack | Architecture / BE | Should | N | Thiên Long | Tùng Chi | 2.0 | 2026-10-21 | 2026-10-23 | W2.08 draft (soft) | NOT STARTED
W2.10 | W2 | UI flow/wireframe Upload → Status → Transcript & mock-fixture draft | Frontend | Should | N | Tùng Chi | Bách Sỹ | 3.0 | 2026-10-20 | 2026-10-23 | Schema nháp; mock-first | NOT STARTED
W2.11 | W2 | Repo & GitHub Project baseline: access, PR rules, secret scan | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long | 2.0 | 2026-10-20 | 2026-10-21 | Không chờ AI pipeline | NOT STARTED
W2.12 | W2 | Local runtime + Docker/CI skeleton, env templates an toàn | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long | 2.0 | 2026-10-21 | 2026-10-23 | W2.11 (soft) | NOT STARTED
W2.13 | W2 | G1 acceptance / QC strategy; Owner–Reviewer–Tester và evidence template | BA / QC | Must | Y | Bách Sỹ | Đức, Thiên Long | 1.0 | 2026-10-22 | 2026-10-23 | Charter baseline | NOT STARTED
W2.14 | W2 | G1 review với CEO/Sponsor, chốt action còn mở & start W3 | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-10-23 | 2026-10-23 | Các bằng chứng M1 / G1 | NOT STARTED
W2.15 | W2 | Chốt framework, version và environment | Architecture / BE | Should | Y | Thiên Long | Bách Sỹ, Hải Đăng | 2.0 | 2026-10-21 | 2026-10-25 | Các lib và độ ổn định | NOT STARTED

## Week 3
KẾ HOẠCH W2–W4 • Work Package level • Action Plan chi tiết sẽ lập riêng theo từng tuần và theo dõi trên GitHub Projects
ID | Tuần | Work Package | Workstream | Ưu tiên | Gate-Critical | Owner (R) | Hỗ trợ | Effort (MD) | Start Date | End Date | Phụ thuộc / điều kiện | Status | Evidence Link | GitHub Issue
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED
W3.01 | W3 | Chốt Job/Transcript canonical schema v0.1, JSON fixtures & adapter interface | Architecture / BE | Must | Y | Thiên Long | Lê Huy, Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | W2.08; không chờ model thật | NOT STARTED
W3.02 | W3 | Backend skeleton: upload/job/status/transcript mock APIs | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.01 fixture (soft) | NOT STARTED
W3.03 | W3 | Làm sạch sample audio, metadata, rights & versioned ground truth | Data & Evaluation | Must | Y | Trọng Nhân | Lê Huy | 2.0 | 2026-10-26 | 2026-10-28 | W2.04/W2.05 | NOT STARTED
W3.04 | W3 | Tạo hội thoại TTS/role-play ban đầu, speaker/timestamp labels mẫu | Data & Evaluation | Must | N | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-10-28 | 2026-10-30 | Scripts/GT template W2 | NOT STARTED
W3.05 | W3 | PoC VAD + ASR primary candidate trên audio thử nghiệm | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2.0 | 2026-10-26 | 2026-10-28 | Audio public hoặc mock hợp lệ | NOT STARTED
W3.06 | W3 | PoC diarization, timestamps và đặc trưng âm học (librosa) | Speech AI / OSS | Must | N | Lê Huy | Hải Đăng | 2026-05-02 | 2026-10-28 | 2026-10-30 | W3.05 không bắt buộc hoàn tất | NOT STARTED
W3.07 | W3 | Policy/checklist v0.1: policy refs, expected QA fixture | BA / Policy | Must | Y | Bách Sỹ | Đức, Trọng Nhân | 2026-05-02 | 2026-10-26 | 2026-10-29 | W2.02/W2.03 | NOT STARTED
W3.08 | W3 | Contract testing, Unit Test policy và test evidence template | BA / QC | Must | Y | Bách Sỹ | Thiên Long | 2.0 | 2026-10-29 | 2026-10-30 | W3.01 draft fixtures | NOT STARTED
W3.09 | W3 | Frontend skeleton Upload / Status / Transcript từ mock fixture | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-10-26 | 2026-10-29 | Mock từ W2; schema v0.1 | NOT STARTED
W3.10 | W3 | FE error/loading states, mock contract compatibility smoke | Frontend | Should | N | Tùng Chi | Bách Sỹ | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.09 | NOT STARTED
W3.11 | W3 | Docker/Compose: BE mock, AI worker adapter runtime, CI smoke | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Lê Huy | 3.0 | 2026-10-26 | 2026-10-29 | W2.12; mock worker trước | NOT STARTED
W3.12 | W3 | Central env/logging & integration health checks; không commit secrets | Platform / DevOps | Must | N | Hải Đăng | Thiên Long | 2026-05-01 | 2026-10-29 | 2026-10-30 | W3.11 | NOT STARTED
W3.13 | W3 | Rà blocker, OSS shortlist + backups, chuẩn bị G2 evidence register | PM / Governance | Must | N | Đức | Lê Huy, Bách Sỹ | 2.0 | 2026-10-28 | 2026-10-30 | PoC chạy song song; trạng thái proposed | NOT STARTED

## Week 4
KẾ HOẠCH W2–W4 • Work Package level • Action Plan chi tiết sẽ lập riêng theo từng tuần và theo dõi trên GitHub Projects
ID | Tuần | Work Package | Workstream | Ưu tiên | Gate-Critical | Owner (R) | Hỗ trợ | Effort (MD) | Start Date | End Date | Phụ thuộc / điều kiện | Status | Evidence Link | GitHub Issue
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED
W4.01 | W4 | Chốt data card, test split, provenance, license & GT mẫu | Data & Evaluation | Must | Y | Trọng Nhân | Bách Sỹ | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.03; không phụ thuộc model | NOT STARTED
W4.02 | W4 | Thêm synthetic/role-play hard cases, ghi rõ giới hạn dữ liệu | Data & Evaluation | Should | N | Trọng Nhân | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W3.04 | NOT STARTED
W4.03 | W4 | So sánh primary/backup VAD & ASR, WER/CER baseline và tài nguyên | Speech AI / OSS | Must | Y | Lê Huy | Trọng Nhân | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.05 + test set v0.1 | NOT STARTED
W4.04 | W4 | Diarization & Emotion-feasibility evidence: observable signals / giới hạn | Speech AI / OSS | Must | Y | Lê Huy | Bách Sỹ | 2.0 | 2026-11-04 | 2026-11-06 | W3.06; không bắt buộc emotion classifier | NOT STARTED
W4.05 | W4 | Model adapter → Transcript contract: valid/invalid fixture tests | Architecture / BE | Must | Y | Thiên Long | Lê Huy | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.01 + output AI hoặc fake response | NOT STARTED
W4.06 | W4 | Backend mock→real smoke, job status/error paths & transcript response | Architecture / BE | Must | Y | Thiên Long | Hải Đăng | 2.0 | 2026-11-04 | 2026-11-06 | W4.05 (soft; mock fallback) | NOT STARTED
W4.07 | W4 | FE Upload / Status / Transcript kết nối API mock hoặc real | Frontend | Must | N | Tùng Chi | Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.09; mock path ưu tiên | NOT STARTED
W4.08 | W4 | FE smoke: empty/error/loading & evidence-ready UI placeholder | Frontend | Should | N | Tùng Chi | Bách Sỹ | 1.0 | 2026-11-05 | 2026-11-06 | W4.07 | NOT STARTED
W4.09 | W4 | Compose integration smoke (API+worker+FE), trace logs & replay mock | Platform / DevOps | Must | Y | Hải Đăng | Thiên Long, Tùng Chi | 2026-05-02 | 2026-11-02 | 2026-11-04 | W3.11; mocked service chấp nhận | NOT STARTED
W4.10 | W4 | CI build/test/security checks; backup runtime switch rehearsal | Platform / DevOps | Must | N | Hải Đăng | Lê Huy | 2.0 | 2026-11-04 | 2026-11-06 | W4.09, OSS candidate config | NOT STARTED
W4.11 | W4 | Checklist/policy/evidence sample & QC test pack phục vụ G2 | BA / QC | Must | Y | Bách Sỹ | Trọng Nhân, Thiên Long | 3.0 | 2026-11-02 | 2026-11-05 | W3.07; policy có version | NOT STARTED
W4.12 | W4 | G2 review evidence: data, OSS/license, backups, contracts, smoke test | BA / QC | Must | Y | Bách Sỹ | Lê Huy, Hải Đăng | 2026-05-01 | 2026-11-05 | 2026-11-06 | W4.01–W4.11 (evidence) | NOT STARTED
W4.13 | W4 | ADR shortlist primary/backup và phương án W5–W6 khi blocker | PM / Governance | Must | Y | Đức | Thiên Long, Lê Huy | 1.0 | 2026-11-05 | 2026-11-06 | G2 evidence; có thể DEFERRED | NOT STARTED
W4.14 | W4 | G2 review CEO/Sponsor; quyết định readiness & M3 next steps | PM / Gate | Must | Y | Đức | Bách Sỹ, cả team | 1.0 | 2026-11-06 | 2026-11-06 | W4.12/W4.13; review có điều kiện | NOT STARTED

## Milestone & Gate Tracker
IX.VOICE / MILESTONE & GATE TRACKER
CURRENT WBS WINDOW: M1 / G1 (W1–W2) + M2 / G2 (W3–W4) ¦ M3–M7 chỉ là mốc tham chiếu Project Charter, chưa phải WBS chi tiết
TỔNG WORK PACKAGES |  |  | EFFORT DỰ KIẾN (MD) |  |  | MUST WPs |  |  | BLOCKED WPs
41 |  |  | 84.5 |  |  | 36 |  |  | 0
TỔNG QUAN MILESTONE CHARTER • M1–M7 (mốc W5–W16 chỉ để định hướng, không phân rã task trong file này)
Milestone | Thời gian | Outcome chính | Gate | Trạng thái | Phạm vi WBS |  | NGUYÊN TẮC: KHÔNG TẠO CHUỖI BLOCKING
M1 — Initiation | W1–W2 | Charter, team/scope, Data/Policy inventory, OSS research sớm | G1 | IN PROGRESS | WBS 01 — SƠ BỘ |  | Các workstreams Data, Speech AI, BE, FE, DevOps, BA/QC chạy song song từ sớm. Khi thiếu model/dataset thật, sử dụng fixtures/mock có version và nêu trạng thái mock/real minh bạch.
M2 — Baseline & Feasibility | W3–W4 | Repo/CI, contracts/fixtures, OSS PoC primary+backup, G2 evidence | G2 | PLANNED | WBS 01 — SƠ BỘ
M3 — E2E Slice | W5–W6 | Upload → processing → transcript/speaker → QA/UI | G3 | FUTURE | WBS 02 (lập sau G2)
M4 — AI/Business Features | W7–W10 | Summary, meeting minutes, checklist/policy/evidence, emotion signals | G4 | FUTURE | Kế hoạch rolling-wave |  | GATE LÀ ĐIỂM RA QUYẾT ĐỊNH, KHÔNG PHẢI LỆNH DỪNG TOÀN BỘ DỰ ÁN. Gate chưa đạt phải có gap, owner, hạn và phương án backup. CEO/Sponsor review từng Gate.
M5 — Integrated Beta | W11–W12 | QA Review, dashboard/export/API, integration regression | G5 | FUTURE | Kế hoạch rolling-wave
M6 — Release Candidate | W13–W14 | Security, performance, regression, UAT & known issues | G6 | FUTURE | Kế hoạch rolling-wave
M7 — Release & Handover | W15–W16 | MVP v0.1, evidence, handover docs & next roadmap | G7 | FUTURE | Kế hoạch rolling-wave
CHI TIẾT GATE TRONG KỲ WBS HIỆN TẠI • G1 và G2
Gate | Due Date | Milestone | Mục tiêu / Quyết định | Evidence cần review | Owner | Reviewer | Gate Status | Quyết định | Evidence Link | Open Actions | WBS IDs
G1 | 2026-10-23 | M1 / W1–W2 | Xác nhận scope/use case BHNT, team & Charter, WBS W1–W4; research/OSS/data/policy có Owner và kế hoạch. | Charter, danh sách nguồn Data & policy, OSS primary+backup shortlist/licensing preliminary, architecture draft, Risk/Decision Log. | Đức | CEO / Sponsor | PLANNED |  |  | Ghi gap + owner/hạn; approve Action Plan W3 | W2.01–W2.14
G2 | 2026-11-06 | M2 / W3–W4 | Quyết định phương án primary/backup, readiness baseline & PoC; chuẩn bị First E2E Slice (W5–W6). | Schema/fixtures v0.1, repo/CI/Compose, data rights+GT, ASR/VAD/diarization & emotion feasibility, mock→real integration smoke, test pack/known limits. | Đức | CEO / Sponsor | PLANNED |  |  | PASS / PASS WITH ACTIONS / DEFERRED; chốt gap và W5–W6 | W3.01–W4.14
CÁCH SỬ DỤNG • G1/G2 có CEO/Sponsor review; bằng chứng được link thay vì đưa test case và acceptance criteria chi tiết vào WBS.
STATUS WBS: NOT STARTED · IN PROGRESS · IN REVIEW · DONE · BLOCKED · DEFERRED. ƯU TIÊN: Must / Should / Could. ĐƯỜNG GĂNG Y: WP ảnh hưởng trực tiếp shared baseline/Gate (không tự động khóa các công việc song song). Các Gate chưa PASS cần ghi gap, Owner, deadline và ghi nhận quyết định Sponsor.
PHÂN RÃ QUẢN LÝ: Project Charter (16 tuần) → WBS rolling-wave (W1–W4) → Action Plan từng tuần (deliverable, AC, reviewer/tester) → GitHub Projects (Issue, assignee, progress & links). Ngày/Effort trong WBS là dự kiến; Action Plan xác nhận lại với member trước khi thực hiện.